## Iteration-1
DORMITORY MANAGEMENT SYSTEM (DMS)
Group Members: | Nazlı Karalar
İsmetcan Hergünşen
Gamze Küçükçolak
Mehmet Kağan Kayaalp
Erdi Koç
Sprint Backlog
| Product Backlog | [5 empty] | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED
| ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS | PROGRESS | #11 | Design GUI (main page) | Erdi Koç & Nazlı Karalar | 4 | Completed
| #1 | Add student’s personal data | 1 | 8 | In Progress | 70% | #1.1 | Design GUI (add students and info) | Mehmet Kağan Kayaalp | 2 | Completed
| #2 | Remove student’s personal data | 4 | 3 | Not Started |  | #1.2 | Create DB tables for students | Nazlı Karalar | 7 | Completed
| #3 | View the list of students according to the enrolled rooms. | 2 | 6 | Not Started |  | #7.1 | Design GUI (add dorms and rooms) | Erdi Koç | 1 | Completed
| #4 | Keep track of lost and damaged material | 4 | 6 | Not Started |  | #7.2 | Create DB tables for dorms and rooms | Mehmet Kağan Kayaalp | 4 | Completed
| #5 | Enter the fee of the room according to the type of the room | 1 | 2 | Completed | 100% | #7.3 | Add dorm and room | İsmetcan Hergünşen | 2 | Completed
| #6 | Display the students’ debts and payment history | 1 | 4 | Not Started |  | #5 | Enter the fee of the room types | Gamze Küçükçolak | 1 | Completed
| #7 | Add new dormitories and rooms to the list | 1 | 4 | Completed | 100% |  |  | WEEK2 SUM | 21
| #8 | Display accomodation time of students | 2 | 1 | Not Started
| #9 | Filter students with respect to name, surname, student id | 3 | 12 | Not Started | [6 empty] | 65 | 44
| #10 | Search available rooms | 2 | 4 | Not Started
| #11 | Home screen design | 1 | 3 | Completed | 100% | [5 empty] | 65 | 44
| #12 | View students' information | 3 | 2 | Not Started | [6 empty] | 65 | 52
| #13 | Update students' information, rooms, dorms etc. | 3 | 10 | Not Started | [6 empty] | 65 | 48 | 39 | 26 | 13 | 0
|  | TOTAL TIME |  | 65 | [7 empty] | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5
[12 empty] | Product Backlog Items | Estimated Time (hrs) | Actual Time Spend (hrs)
[12 empty] | 1 | 8 | 9
[12 empty] | 7 | 4 | 7
[12 empty] | 5 | 2 | 1
[12 empty] | 11 | 3 | 4
[12 empty] | TOTAL | 17 | 21
Description: DMS is a desktop application which enables dormitory managers to track students living in their dorms.They will be able to enter students' registrations including student's information (names, surnames, e-mails etc), residents' fees, debts and also they can define the room types and their prices. Besides, this program shows the room of the students and their start/end dates of staying in the dorm.

## Iteration-2
DORMITORY MANAGEMENT SYSTEM (DMS)
Group Members: | Nazlı Karalar
İsmetcan Hergünşen
Gamze Küçükçolak
Mehmet Kağan Kayaalp
Erdi Koç
Sprint Backlog
| Product Backlog | [5 empty] | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED
| ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS | PROGRESS | #1.3 | Show students's personal data in DB | Gamze Küçükçolak | 1 | Completed
| #1 | Add student’s personal data | 1 | 8 | Completed | 100% | #1.4 | Adding emergency contacts of a student | Nazlı Karalar | 1 | Completed
| #2 | Remove student’s personal data | 4 | 3 | Not Started |  | #1.5 | Adding accomodation info of a student | Nazlı Karalar | 1 | Completed
| #3 | View the list of students according to the enrolled rooms. | 2 | 6 | In Progress | 60% | #3.1 | Show dorm list | Mehmet Kağan Kayaalp | 2 | Completed
| #4 | Keep track of lost and damaged material | 4 | 6 | Not Started |  | #3.2 | Add room list according to dorms | Nazlı & Gamze | 2 | Completed
| #5 | Enter the fee of the room according to the type of the room | 1 | 2 | Completed | 100% | #7.4 | Add Room Updated | İsmetcan Hergünşen | 1 | Completed
| #6 | Display the students’ debts and payment history | 1 | 4 | Not Started |  | #9.1 | Display student list | Gamze Küçükçolak | 4 | Completed
| #7 | Add new dormitories and rooms to the list | 1 | 4 | Completed | 100% | #14.1 | Showing capacity of room and dorm in a chart | Erdi Koç | 2 | Completed
| #8 | Display accomodation time of students | 2 | 1 | Not Started |  | #1.6 | Add Student Update(new Combobox usage) | İsmetcan Hergünşen | 1 | Completed
| #9 | Filter students with respect to name, surname, student id | 3 | 12 | In Progress | 40% |  |  | WEEK2 SUM | 15 |  |  | 65 | 44
| #10 | Search available rooms | 2 | 4 | Not Started
| #11 | Home screen design | 1 | 3 | Completed | 100% |  |  | New Spring Backlog | 4 |  |  | 65 | 34
| #12 | View students' information | 3 | 2 | Not Started | [7 empty] | 65 | 45
| #13 | Update students' information, rooms, dorms etc. | 3 | 10 | Not Started | [7 empty] | 65 | 48 | 37 | 26 | 13 | 0
| #14 | Show dorm capacity | 3 | 4 | In Progress | 50% | [6 empty] | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5
|  | TOTAL TIME |  | 69
[13 empty] | Product Backlog Items | Estimated Time (hrs) | Actual Time Spend (hrs) | Upgrade
[13 empty] | 1 | 8 | 13 | 4
[13 empty] | 7 | 4 | 8 | 1
[13 empty] | 3 | 6 | 4 | 4
[13 empty] | 9 | 12 | 4 | 4
[13 empty] | 14 | 4 | 2 | 2
[13 empty] | TOTAL | 34 | 31 | 15
[11 empty] | 65 | 65
[11 empty] | 52 | 52
41
Description: DMS is a desktop application which enables dormitory managers to track students living in their dorms.They will be able to enter students' registrations including student's information (names, surnames, e-mails etc), residents' fees, debts and also they can define the room types and their prices. Besides, this program shows the room of the students and their start/end dates of staying in the dorm.

## Iteration-3
DORMITORY MANAGEMENT SYSTEM (DMS)
Group Members: | Nazlı Karalar
İsmetcan Hergünşen
Gamze Küçükçolak
Mehmet Kağan Kayaalp
Erdi Koç
Sprint Backlog
| Product Backlog | [5 empty] | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED
| ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS | PROGRESS | #9.2 | Filter Students according to name and surname | Nazlı Karalar | 3 | Completed
| #1 | Add student’s personal data | 1 | 8 | Completed | 100% | #3.3 | Display students according to the enrolled rooms | GamzeKüçükçolak | 2 | Completed
| #2 | Remove student’s personal data | 4 | 3 | Not Started |  | #12 | View student information on the profile tab | Nazlı Karalar | 2 | Completed
| #3 | View the list of students according to the enrolled rooms. | 2 | 6 | Completed | 100% | #14.2 | Design GUI (chart data type) | İsmetcan Hergünşen | 1 | Completed
| #4 | Keep track of lost and damaged material | 4 | 6 | Not Started |  | #14.3 | Design new GUI (show dorm capacity) | Erdi Koç | 1 | Completed |  |  | 10.8333
| #5 | Enter the fee of the room according to the type of the room | 1 | 2 | Completed | 100% | #14.4 | Check the occupancy of rooms in DB at a given time interval | GamzeKüçükçolak | 2 | Completed
| #6 | Display the students’ debts and payment history | 1 | 4 | Not Started |  | #7.5 | Room No generated automatically | Mehmet Kağan Kayaalp | 1 | Completed
| #7 | Add new dormitories and rooms to the list | 1 | 4 | Completed | 100% | #13 .1 | Edit student information procedures in DB | Gamze Küçükçolak | 3 | Completed |  | 65 | 44
| #8 | Display accomodation time of students | 2 | 1 | Not Started |  | #13.2 | Edit student information on the profile tab | Mehmet Kağan Kayaalp | 1 | Completed
| #9 | Filter students with respect to name, surname, student id | 3 | 12 | Completed | 100% | #14.4 | Display female/male capacity of the dorms | Erdi Koç & İsmetcan | 2 | Completed |  | 65 | 48
| #10 | Search available rooms | 2 | 4 | Not Started |  |  |  | WEEK2 SUM | 18 |  |  | 65 | 56.1667 | 41 | 25
| #11 | Home screen design | 1 | 3 | Completed | 100% | [6 empty] | 65 | 54.1667 | 43.3333 | 32.5 | 21.6667 | 10.8333 | 0
| #12 | View students' information | 3 | 2 | Completed | 100% | [6 empty] | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | WEEK6
| #13 | Update students' information | 3 | 5 | Completed | 100%
| #14 | Show dorm capacity | 4 | 4 | In Progress | 60%
| #15 | Update dorms and rooms | 4 | 5 | Not Started | [7 empty] | Product Backlog Items | WEEK1: Estimated Time (hrs); WEEK2: Actual Time Spend (hrs); WEEK3: Upgrade
|  | TOTAL TIME |  | 69 | [8 empty] | 3 | WEEK1: 0; WEEK2: 2; WEEK3: -2
[13 empty] | 7 | WEEK1: 0; WEEK2: 1; WEEK3: -1
[13 empty] | 9 | WEEK1: 8; WEEK2: 3; WEEK3: 5
[13 empty] | 12 | WEEK1: 2; WEEK2: 2; WEEK3: 0
[13 empty] | 13 | WEEK1: 5; WEEK2: 4; WEEK3: 1
[13 empty] | 14 | WEEK1: 0; WEEK2: 5; WEEK3: -5
[13 empty] | TOTAL | WEEK1: 15; WEEK2: 17; WEEK3: -2
[11 empty] | 65 | 65
[11 empty] | 52 | 52
Description: DMS is a desktop application which enables dormitory managers to track students living in their dorms.They will be able to enter students' registrations including student's information (names, surnames, e-mails etc), residents' fees, debts and also they can define the room types and their prices. Besides, this program shows the room of the students and their start/end dates of staying in the dorm.

## Iteration-4
DORMITORY MANAGEMENT SYSTEM (DMS)
Group Members: | Nazlı Karalar
İsmetcan Hergünşen
Gamze Küçükçolak
Mehmet Kağan Kayaalp
Erdi Koç
Sprint Backlog
| Product Backlog | [5 empty] | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED
| ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS | PROGRESS | #9.3 | Filter students with respect to name | Nazli Karalar | 1 | Completed
| #1 | Add student’s personal data | 1 | 8 | Completed | 100% | #13.3 | Dorm and room can be changed | Gamze Küçükçolak | 1 | Completed
| #2 | Remove student’s personal data | 4 | 3 | Not Started |  | #14.5 | Dorm capacity chart | Erdi Koç & İsmetcan | 2 | Completed
| #3 | View the list of students according to the enrolled rooms. | 2 | 6 | Completed | 100% | #4.1 | Add Damaged Item GUI | Nazli Karalar | 1 | Completed
| #4 | Keep track of lost and damaged material | 4 | 6 | Completed | 100% | #4.2 | Add Lost Item GUI | Gamze Küçükçolak | 1 | Completed |  |  | 10.8333
| #5 | Enter the fee of the room according to the type of the room | 1 | 2 | Completed | 100% | #4.3 | Items List GUI | Nazli Karalar | 1 | Completed
| #6 | Display the students’ debts and payment history | 1 | 4 | In Progress | 30% | #4.4 | Damaged/Lost/Closed Items Procedures | Gamze Küçükçolak | 2 | Completed
| #7 | Add new dormitories and rooms to the list | 1 | 4 | Completed | 100% | #4.5 | Closed Item GUI | Ismetcan Hergünsen | 1 | Completed |  | 65 | 44
| #8 | Display accomodation time of students | 2 | 1 | Completed | 100% | #4.6 | Lost and Damaged Items can be closed | Nazli Karalar & Erdi Koç | 2 | Completed
| #9 | Filter students with respect to name, surname, student id | 3 | 12 | Completed | 100% | #15.1 | Male/Female Chart | Erdi Koç & Gamze | 1 | Completed |  | 65 | 51
| #10 | Search available rooms | 2 | 4 | Not Started |  | #6.1 | Payment GUI | Kağan Kayaalp | 1 | Completed |  | 65 | 58.1667 | 41 | 25 | 15
| #11 | Home screen design | 1 | 3 | Completed | 100% |  |  | WEEK2 SUM | 14 |  |  | 65 | 54.1667 | 43.3333 | 32.5 | 21.6667 | 10.8333 | 0
| #12 | View students' information | 3 | 2 | Completed | 100% | [6 empty] | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | WEEK6
| #13 | Update students' information | 3 | 5 | Completed | 100%
| #14 | Show dorm capacity | 4 | 4 | Completed | 100%
| #15 | Show male/female capacity | 4 | 3 | In Progress | 80% | [6 empty] | Product Backlog Items | WEEK1: Estimated Time (hrs); WEEK2: Actual Time Spend (hrs); WEEK3: Upgrade
| #16 | Update dorms and rooms | 4 | 5 | Not Started | [7 empty] | 4 | WEEK1: 6; WEEK2: 8; WEEK3: -2
|  | TOTAL TIME |  | 72 | [8 empty] | 6 | WEEK1: 4; WEEK2: 1; WEEK3: 3
[13 empty] | 9 | WEEK1: 0; WEEK2: 1; WEEK3: -1
[13 empty] | 13 | WEEK1: 0; WEEK2: 1; WEEK3: -1
[13 empty] | 14 | WEEK1: 0; WEEK2: 1; WEEK3: -1
[13 empty] | 15 | WEEK1: 0; WEEK2: 2; WEEK3: -2
[13 empty] | TOTAL | WEEK1: 10; WEEK2: 14; WEEK3: -4
[11 empty] | 65 | 65
[11 empty] | 52 | 52
Description: DMS is a desktop application which enables dormitory managers to track students living in their dorms.They will be able to enter students' registrations including student's information (names, surnames, e-mails etc), residents' fees, debts and also they can define the room types and their prices. Besides, this program shows the room of the students and their start/end dates of staying in the dorm.