## Sheet1
Group Members: | Nazlı Karalar
İsmetcan Hergünşen
Gamze Küçükçolak
Mehmet Kağan Kayaalp
Erdi Koç
Product Backlog
| ID | STORY | PRIORTY | TIME ESTIMATION (hours) | STATUS | Sprint Backlog
| #1 | add student’s personal data | 1 | 5 | Not Started | ID | STORY | RESPONSIBLE PERSON | TIME ESTIMATION | COMPLETED
| #2 | remove student’s personal data | 4 | 3 | Not Started | #14 | Design GUI (main page) | Erdi Koç & Nazlı Karalar | 4 | Not Completed
| #3 | view the list of students according to the enrolled rooms. | 2 | 6 | Not Started | #1.1 | Design GUI (add students and info) | Mehmet Kağan Kayaalp | 1 | Not Completed
| #4 | keep track of lost and damaged material | 4 | 6 | Not Started | #1.2 | Create DB tables for students | Nazlı Karalar | 2 | Not Completed
| #5 | enter the fee of the room according to the type of the room | 1 | 2 | Not Started | #1.3 | Add student | Gamze Küçükçolak | 2 | Not Completed
| #6 | display the students’ debts and payment history | 1 | 4 | Not Started | #7.1 | Design GUI (add dorms and rooms) | Erdi Koç | 1 | Not Completed
| #7 | add new dormitories and rooms to the list | 1 | 3 | Not Started | #7.2 | Create DB tables for dorms and rooms | Mehmet Kağan Kayaalp | 1 | Not Completed
| #8 | display accomodation time of students | 2 | 1 | Not Started | #7.3 | Add dorm and room | İsmetcan Hergünşen | 1 | Not Completed
| #9 | filter students with respect to name, surname, student id | 3 | 12 | Not Started | #5 | Enter the fee of the room types | Gamze Küçükçolak | 2 | Not Completed
| #10 | search available rooms | 2 | 4 | Not Started | #11 | Logo design | İsmetcan Hergünşen | 3 | Not Completed
| #11 | logo design | 5 | 3 | Not Started
| #12 | view students' information | 3 | 2 | Not Started |  |  | WEEK2 SUM | 17
| #13 | update students' information, rooms, dorms etc. | 4 | 10 | Not Started
| #14 | home screen design | 1 | 4 | Not Started | [5 empty] | 65 | 52 | 39 | 26 | 13 | 0
[5 empty] | Not Started | [5 empty] | START | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5
|  | TOTAL TIME |  | 65